## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Setup project environment & install libraries (pandas, numpy, torch) | MUST HAVE | No Dependency | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S1 | S1 | US-001 | Connect to enterprise data sources | MUST HAVE | Data Access Credentials | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S1 | S1 | US-001 | Build data ingestion pipeline | MUST HAVE | No Dependency | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S1 | S1 | US-001 | Clean and normalize data | MUST HAVE | Ingestion Pipeline | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S1 | S1 | US-001 | Define knowledge graph schema | MUST HAVE | Neo4j | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S1 | S1 | US-001 | Validate ingestion workflow | MUST HAVE | Schema Definition | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S2 | S2 | US-001 | Apply LLM-based NER for entity extraction | MUST HAVE | LLM API (OLLAMA) | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S2 | S2 | US-001 | Extract relationships from data | MUST HAVE | NER Model | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S2 | S2 | US-001 | Store entities/relationships in Neo4j | MUST HAVE | Neo4j | Ansh Pratap Singh, Pachagnula Swastik,Vasudha | 3- Completed
S2 | S2 | US-001 | Build and validate graph structure in Neo4j | MUST HAVE | Neo4j | Ansh Pratap Singh, Pachagnula Swastik,Vasudha | 3- Completed
S2 | S2 | US-001 | Create project folder structure | MUST HAVE | No Dependency | Ansh Pratap Singh, Pachagnula Swastik,Vasudha | 3- Completed
S2 | S2 | US-001 | Install required libraries (pandas, numpy, torch) | MUST HAVE | No Dependency | Ansh Pratap Singh, Pachagnula Swastik,Vasudha | 3- Completed
S3 | S3 | US-001 | Integrate embedding model (sentence-transformers) | MUST HAVE | Transformer Model | Ansh Pratap Singh, Pachagnula Swastik,Vasudha | 3- Completed
S3 | S3 | US-001 | Connect Pinecone/FAISS vector store | MUST HAVE | Pinecone/FAISS | Ansh Pratap Singh, Pachagnula Swastik,Vasudha | 3- Completed
S3 | S3 | US-001 | Build semantic search pipeline | SHOULD HAVE | Vector Store | Ansh Pratap Singh, Pachagnula Swastik,Vasudha | 3- Completed
S3 | S3 | US-001 | Implement RAG pipeline | MUST HAVE | LLM + Vector Store | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S3 | S3 | US-001 | Test retrieval accuracy and optimize prompts | SHOULD HAVE | RAG Pipeline | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S3 | S3 | US-001 | Optimize query performance | MUST HAVE | Vector Store | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S4 | S4 | US-001 | Build graph visualization UI (Neo4j ) | MUST HAVE | Neo4j Browser | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S4 | S4 | US-001 | Create interactive dashboard (Streamlit) | MUST HAVE | Flask | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S4 | S4 | US-001 | Integrate APIs (FastAPI ) | MUST HAVE | HuggingFaceAPI | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S4 | S4 | US-001 | End-to-end testing and bug fixing | MUST HAVE | All Modules | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
S4 | S4 | US-001 | Deploy system to production (Docker/Cloud) | MUST HAVE | Render | Ansh Pratap Singh, Pachagnula Swastik | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 13.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Setup project environment & install libraries | 2026-02-02 | 2026-02-03 | Ansh and Swastik | Build | 3- Completed | 2
US-002 | 2 | Connect to enterprise data sources | 2026-02-04 | 2026-02-05 | Ansh and Swastik | Coding | 3- Completed | 3
US-003 | 3 | Build data ingestion pipeline | 2026-02-06 | 2026-02-07 | Ansh and Swastik | Coding | 3- Completed | 3
US-004 | 4 | Clean and normalize data | 2026-02-09 | 2026-02-10 | Ansh and Swastik | Coding | 3- Completed | 2.5
US-005 | 5 | Define knowledge graph schema | 2026-02-11 | 2026-02-12 | Ansh and Swastik | Others | 3- Completed | 1
US-006 |  | Validate ingestion workflow | 2026-02-12 | 2026-02-13 | Ansh and Swastik | System Test | 3- Completed | 2
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Library installation errors - Ansh Pratap | Resolved by pinning compatible versions in requirements.txt
Sprint 1 | Day 3 | Slow data source connection due to firewall - Ansh Pratap | Coordinated with IT to whitelist required endpoints
Sprint 1 | Day 6 | Ambiguity in knowledge graph schema - Ansh Pratap | Held design review; finalized schema with mentor
Sprint 2 | Day 8 | LLM API rate limits slowing NER - Ansh Pratap, Swastik, Vasudha | Team implemented batching and exponential backoff strategy
Sprint 2 | Day 10 | Neo4j connection issues in dev env - Ansh Pratap, Swastik, Vasudha | Team switched to local Neo4j Desktop instance
Sprint 2 | Day 12 | Graph validation: missing relationships - Ansh Pratap, Swastik, Vasudha | Team re-ran extraction pipeline with refined LLM prompts
Sprint 3 | Day 16 | Pinecone index config errors - Ansh Pratap, Swastik, Vasudha | Team reconfigured index dimensions and tested with sample
Sprint 3 | Day 20 | RAG pipeline low accuracy - Ansh Pratap, Swastik, Vasudha | Team tuned chunk size and overlap; improved prompt templates
Sprint 4 | Day 24 | Dashboard slow with large graph - Ansh Pratap, Swastik, Vasudha | Team added pagination and lazy-loading to visualization
Sprint 4 | Day 28 | API errors: FastAPI and Neo4j - Ansh Pratap, Swastik, Vasudha | Fixed async query handling; added connection pooling as a team
Sprint 4 | Day 32 | Deployment failing on cloud - Ansh Pratap, Swastik, Vasudha | Team updated Docker config and added secrets management
Sprint 4 | Day 36 | Documentation incomplete - Ansh Pratap, Swastik, Vasudha | All 3 members contributed; documentation completed by

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-13 | Ansh Pratap Singh | Daily schema validation checks | Skipping code reviews under time pressure | Documenting all pipeline decisions | All 6 tasks completed. Ingestion pipeline and schema validated
2 | Sprint 2 | 2026-02-14 | 2026-02-27 | Ansh, Swastik, Vasudha | Regular Neo4j graph integrity checks as a team | Delaying Neo4j commits to end of sprint | Team pair debugging NER and extraction issues | All 6 tasks completed by active team. Entities extracted and stored in Neo4j; graph validated.
3 | Sprint 3 | 2026-02-28 | 2026-03-13 | Ansh, Swastik, Vasudha | Early embedding benchmarking before integration | Rushing RAG prompt design without team review | Team semantic search testing and collaboration | All 6 tasks completed by active team. Semantic search and RAG pipeline functional and optimized
4 | Sprint 4 | 2026-03-14 | 2026-03-26 | Ansh, Swastik, Vasudha | CI/CD pipeline and deployment setup early as a team | Late-stage environment variable configuration | Cross-team API review and debugging sessions | All 6 tasks completed by active team. Dashboard deployed; documentation finalized
5 | All Sprints | 2026-02-02 | 2026-03-26 | Ansh, Swastik, Vasudha | Active participation and task ownership in future projects | Non-participation in coding, testing, and collaboration tasks | Attending stand-up meetings (if applicable) | Madhuri and Siri were listed as team members but did not contribute to any tasks across all 4 milestones (0 hours logged). No deliverables completed
6
7